## Leht1
Functionality to be verified | Assignee | Usage frequency of the functionality | Possible damage for business on failure | Priority | Estimated test effort in person-hours
Registering new Purchase (FR1) | Patrik | High | High | High | 1 hour
Overview of warehouse (FR2) | Kristo | High | High | High | 30 minutes
History of all purchases (FR3) | Kristo | Average | High | High | 30 minutes
To see info about the team leader (FR4) | Tauno | Average | High | Average | 20 minutes
Confirming the purchase (FR5) | Patrik | High | High | High | 30 minutes
Entering product to shopping cart (FR6) | Tauno | High | High | High | 1 hour
Same added items to sum up in shopping cart (FR7) | Tauno | Average | Average | Average | 30 minutes
Error if the desired quantity of a product exceeds maximum quantity (FR8) | Tauno | High | High | High | 20 minutes
Adding products to warehouse (FR9) | Patrik | High | High | High | 1 hour
Filtering warehouse objects (FR10) | Patrik | Average | Low | Average | 45 minutes
Deleting products from warehouse (FR11) | Patrik | High | High | High | 1 hour
Showing history on specific dates (FR12) | Kristo | Average | Average | Average | 30 minutes
Option to see last 10 purchases under history (FR13) | Kristo | Average | Low | Low | 30 minutes
Canceling purchase (FR14) | Tauno | High | High | High | 45 minutes
Updating warehouse status after purchase (FR15) | Patrik | High | High | High | 45 minutes
Purchase history to show date, time and how much of some product was sold (FR16) | Kristo | Average | High | High | 30 minutes
In CLI to see what different commands do (FR17) | Kristo | High | High | High | 20 minutes
Manually refreshing and updating the products in warehouse (FR18) | Patrik | Average | High | High | 45 minutes
Show team members names (FR19) | Tauno | Low | Average | Average | 20 minutes
Removing products from shopping cart (FR20) | Tauno | High | High | High | 1 hour
Usage frequency: high - used more than 3 times a day.
Usage frequency: average - used 2-3 times a day.
Usage frequency: low - used 1 time a day or less.
Possible damage for business on failure: high- can't continue working should be fixed right away.
Possible damage for business on failure: average- this doesn't stop the applications other functionalities but it should be fixed soon.
Possible damage for business on failure: low- doesn't really change much because it's replacable with other functionalities