## Leht1
Functionality to be verified | Assignee | Usage frequency of the functionality | Possible damage for business on failure: | Priority | Estimated test effort in person-hours
Registering new Purchase (FR1) | Kristo | High | High | High | 1 hour
Overview of warehouse (FR2) | Kristo | High | High | High | 30 minutes
History of all purchases (FR3) | Kristo | Average | High | High | 30 minutes
To see info about the team leader (FR4) | Tauno | Average | High | Average | 20 minutes
Confirming the purchase (FR5) | Kristo | High | High | High | 30 minutes
Entering product to shopping cart (FR6) | Tauno | High | High | High | 1 hour
Same added items to sum up in shopping cart (FR7) | Tauno | Average | Average | Average | 30 minutes
Error if the desired quantity of a product exceeds maximum quantity (FR8) | Tauno | High | High | High | 20 minutes
Adding products to warehouse (FR9) | Patrik | High | High | High | 1 hour
Filtering warehouse objects (FR10) | Patrik | Average | Low | Average | 45 minutes
Deleting products from warehouse (FR11) | Patrik | High | High | High | 1 hour
Showing history on specific dates (FR12) | Kristo | Average | Average | Average | 30 minutes
Option to see last 10 purchases under history (FR13) | Kristo | Average | Low | Low | 30 minutes
Canceling purchase (FR14) | Kristo | High | High | High | 45 minutes
Updating warehouse status after purchase (FR15) | Patrik | High | High | High | 45 minutes
Purchase history to show date, time and how much of some product was sold (FR16) | Kristo | Average | High | High | 30 minutes
In CLI to see what different commands do (FR17) | Kristo | High | High | High | 20 minutes
Manually refreshing and updating the products in warehouse (FR18) | Patrik | Average | High | High | 45 minutes
Show team members names (FR19) | Tauno | Low | Average | Average | 20 minutes
Removing products from shopping cart (FR20) | Tauno | High | High | High | 1 hour
GUI with compability for all main operating systems (MacOSX, Windows, Linux) (NFR 1) | Tauno | High | High | High | 30 minutes
GUI window to be fixed size (NFR 2) | Patrik | Average | Low | Average | 15 minutes
GUI to be ready for work when opened (NFR 3) | Tauno | High | High | High | 15 minutes
All functions to be available through CLI and GUI (NFR 4) | Patrik | High | High | High | 1 hour and 30 minutes
System to be in English language (NFR 5) | Patrik | High | High | High | 10 minutes
Updating the cart contents in under 150ms 90% of the time when new purchases are added (Performance 1) | Patrik | High | Average | High | 1 hour and 15 minutes
Displaying the view in under 200ms for 90% of the cases when the view is switched to another view (Performance 2) | Tauno | Average | Average | Average | 1 hour and 15 minutes
Dropdown list "Name" displayed to roll down in under a second 95% of the time when clicked (Performance 3) | Tauno | Average | Low | Average | 1 hour and 15 minutes
Purchase to register in under a second for 95% of the cases when it is submitted for registration (Performance 4) | Patrik | High | Average | High | 1 hour and 15 minutes
The application to update the purchase history in under 150ms for 90% of the cases when specific dates are added for the purchase history request (Performance 5) | Patrik | High | Average | High | 1 hour and 15 minutes